## Feature Status
Sprint | Feature | Description | Status | Notes / Implementation Detail (verified 2026-09-06)
1 | User Registration | Auto-generates unique student and tutor IDs, validates input using Zod, hashes passwords with Bcrypt, and captures Data Privacy Act consent during sign-up via a dedicated registration form. | Complete | Unified RegisterForm + POST /api/register (Zod discriminated union, atomic STU-/TUT- IDs, Bcrypt, consentGiven, TutorProfile in the same txn, registrationOpen gate). Password-reset flow added: /forgot-password + /reset-password, hashed single-use PasswordResetToken, link emailed via src/lib/mail.ts (SMTP, console fallback).
1 | User Login/Logout | Handles user authentication through NextAuth's credentials provider, using JWT-based sessions and Bcrypt password comparison for secure login and logout. | Complete | NextAuth credentials + JWT, Bcrypt compare (src/lib/auth.ts). PENDING accounts routed to /pending-approval, DECLINED to /account-declined. Sign-out clears the chat transcript from localStorage.
1 | Route Protection / Proxy Middleware | Enforces server-side role validation across all portals and API routes to prevent unauthorized access. | Complete | src/proxy.ts edge middleware guards /admin, /tutor, /learner; every API route re-checks getServerSession + role. Dev-only /dev and /api/dev hard-404 when NODE_ENV=production.
1 | Account Management for Tutor and Learner | Allows tutors and learners to view and update their account details, including profile information and credentials, after registration. | Complete | Both roles: read-only /learner/profile and /tutor/profile, plus a dedicated edit page /{role}/profile/edit (mirrors class editing). Self-service grade level, section and contact info (PH-mobile validation, src/lib/contactInfo.ts); password reset by emailed link. Real name / email stay admin-only by design (double-blind identity anchor). Tutor profile also lists verified topics.
2 | Class Management for Tutor | Provides a UI for tutors to create, view, update, and delete classes, supporting both one-on-one and group (one-to-many) tutoring sessions. | Complete | Full CRUD, multi-session classes, publish/unpublish, capacity limits, cross-class schedule-conflict checks, status cascade to sessions. Certification gating restricts the topic picker to the tutor's certified topics when the platform requires it. Class moderation + a tutor appeal channel. Finished (COMPLETED) classes are read-only; suspended/banned classes lock every action.
2 | Class Browsing for Learners | Lets learners search and browse available classes, with filters by topic, schedule, and subject. | Complete | /learner/classes browse + detail pages, a global quick-search (Cmd/Ctrl+K, role-scoped: classes / tutors / topics / class requests), and a dedicated /learner/tutors directory (filter by anon ID + subject). Verified-topic pills, tutor profile view, auto-reinstatement of expired suspensions. An unpublished class shows enrolled learners a placeholder instead of full detail.
2 | Learner Class Enrollment | Enables learners to enroll in or unenroll from a tutor's class. | Complete | POST + DELETE /api/classes/[classId]/enroll with every edge case (not SCHEDULED / not published, no upcoming session, full, already enrolled, unenroll blocked on completed/cancelled). Enrol and drop fire tutor notifications (CLASS_ENROLLMENT_NEW / _DROPPED). Route tests present.
2 | Schedule Table for Tutor and Learner | Displays a schedule table showing each user's upcoming and ongoing classes. | Implemented | Tutor: a Mon-Sun WeeklyTimetable on /tutor (next 7 days, session chips linking to the class) plus a derived weekly-availability view on the public profile. Learner: an upcoming-sessions list on /learner, per-class session lists, and /learner/progress. No single combined learner timetable page yet.
2 | Student Management for Tutors | Allows tutors to manage the list of learners enrolled in their classes. | Complete | /tutor/students aggregated roster across all the tutor's classes, per-enrolment subject/topic/date detail, filters (grade / section / subject / class), pagination, profile drill-in. The 'Enrolled In' column now shows the class code.
3 | Automatic Tutor Matching | Matches learners with suitable tutors using a weighted scoring algorithm based on subject, topic, grade level, and schedule compatibility, presented through a dedicated UI. | Complete | src/lib/matching.ts rankMatches() - weighted score on subject (hard filter), requested topics, verified topics, grade compatibility (exact / adjacent / any) and schedule fit, with a SOLO / GROUP / ANY format preference. /learner/match MatchFinder UI with a form<->results swap. Admin kill switch (matchingEnabled).
3 | Topic Request for Learners | Allows learners to submit a request specifying their desired topic, subject, and preferred schedule when no suitable tutor match is found. | Complete | Full lifecycle OPEN -> ACCEPTED -> ENROLLED -> FULFILLED with re-open on cancel; public vs directed-to-one-tutor; a tutor accepts it and the system auto-creates the class (certified topics only); DB-backed notifications; admin moderation queue (/admin/topic-requests). Tutor browser has Directed / Public / Accepted tabs. Renamed 'topic request' -> 'class request' in all UI copy (2026-09-06).
4 | Topic Assessment for Tutor | Evaluates a tutor's subject knowledge for topics they intend to teach; tutors who pass are awarded a badge for that topic, supported by a question bank. | Complete | Admin question bank per subject+topic (/admin/assessment/question-bank) with ONE platform-wide config (question count / pass % / min bank size) on Settings -> Assessment. Auto-graded single-answer MCQ quiz; retakes prefer unseen questions; passing auto-certifies (autoCertifyOnAssessmentPass) or raises a PENDING certification for admin confirmation. A tutor can now start an assessment for ANY topic without owning a class for it. Attempt history + admin per-question results.
4 | Topic Assessment Request for Tutor | Notifies the admin when a tutor creates a class for a topic that has no existing assessment, prompting the admin to create one so all topics remain properly assessed. | Complete | Tutor 'Request questions' on a thin/empty topic -> admin queue (/admin/assessment/requests) AND every active admin is notified (QUESTION_REQUEST_NEW). Divergence: the thesis's automatic trigger on class creation was intentionally replaced by requireCertificationForClassCreation gating plus this manual request path.
4 | Pre- and Post-Test Engine for Classes | Requires tutors to publish pre- and post-session quizzes to measure student understanding and track learning progress. | Complete | Re-grained from one PRE+POST per class to one SessionTest per ClassSession, served twice (kind PRE¦POST on the attempt). Tutor builder (admin bank + self-authored questions, isolated by origin flag), learner take / resume / review, tutor + admin per-question and per-learner pre->post delta reporting. sessionTestsEnabled kill switch. Landed on main with seed data (Changes.md Part 29, phases 0-8).
4 | Learner Progress Report | Provides a before-and-after comparison of learner scores to visualize academic progress. | Complete | Dedicated cross-class /learner/progress (area chart, class filter, summary numbers) + a compact embed on the class page; tutor ClassProgressPanel per class; admin read-only results at /admin/session-tests. Diagnostic only (no pass/fail), per the thesis delimitation.
5 | Chatbot Assistant | Uses intent-based response logic (rule/pattern matching) to identify user requests, offering navigation help, FAQ support, class recommendations, and an interactive chat widget. | Complete | Deterministic intent matcher - tokenise -> keyword / synonym / regex scoring, typo-tolerant, length-normalised confidence gate. No LLM. ~35 role-aware intents, 26-entry grounded FAQ, per-portal floating widget with a localStorage transcript (wiped on logout), learner class-recommendation via rankMatches, admin unmatched-query review (/admin/chatbot). chatbotEnabled kill switch. FAQ KB still pending real TRIS stakeholder interviews.
6 | Tutor Dashboard | Displays a tutor's classes, schedule, and other relevant account information in one view. | Complete | /tutor shows 4 stat cards with icons (topics taught, verified topics, enrolled learners, open class requests), a readable upcoming-sessions list, the Mon-Sun WeeklyTimetable, an onboarding checklist (auto-hides when done) and an assessments summary card.
6 | Learner Dashboard | Displays a learner's classes, schedule, and other relevant account information in one view. | Complete | /learner shows stat cards (enrolled classes, sessions this week, open class requests), an upcoming-sessions list and quick links (browse classes, my classes, find tutors, my class requests, progress).
6 | Admin Dashboard | Presents platform-wide information such as total learners, tutors, and created classes, along with system status and usage statistics. | Complete | /admin overview (counts + pending-action tiles) plus a full analytics page /admin/reports (users by role / grade / status, classes by subject / status, certification breakdown, 30-day enrolment trend, charts) and an AuditLog of every moderation action. Descriptive stats only, per the delimitation.
6 | User Management for Admin | Allows the admin to suspend a class or suspend/ban a tutor or learner account. | Complete | /admin/users + /admin/classes with suspend / ban (+ duration), class suspend / ban, a DECLINED registration state, sortable columns (including a Code column), expired-suspension auto-reinstatement, a full AuditLog, and a tutor class-appeal workflow (/admin/class-appeals with a 'view audit log' link; filing an appeal notifies every admin).
6 | Report Class, Report Tutor, Report Learner | Enables users to submit reports on classes, tutors, or learners, notifying the admin for review. | Not Yet Started | No user-submitted report / flag flow (no model, API or UI). Not one of the six core thesis modules; the governance need is met by admin moderation + AuditLog + the class-appeal channel. Deprioritised.
| TOTALS | 21 features - 19 Complete, 1 Implemented (Schedule Table: tutor timetable done, no combined learner view), 1 Not Yet Started (user-submitted Reports - outside the 6 core modules).
Weighted progress (Complete 1.0 / Implemented 0.8 / Not-started 0.0): 95%.
Prior report (2026-09-02): 3 Complete, 6 Implemented, 7 Partial, 5 Not Yet Started - 54%. All six thesis core modules are now Complete (see docs/feature-checklist.md).
OPEN ITEMS (2026-09-06):
Grow the chatbot FAQ knowledge base from real TRIS stakeholder interviews.
User-submitted 'Report a class / tutor / learner' flow (not started).
Single combined learner timetable page; deployment (see docs/plans/deployment.md).
OPEN QUESTIONS / ANSWERS
| Q (Learner Class Enrollment): | What are the edge cases?
| A - enroll (POST): | 401 if not a logged-in learner; 404 if class not found; 400 if the class is not SCHEDULED or not published; 400 if it has no upcoming SCHEDULED session in the future; 409 if the class is full (enrollments >= maxStudents); 409 if already enrolled; expired class suspensions are auto-reinstated before the checks; 500 on unexpected error.
| A - unenroll (DELETE): | 401 if not a logged-in learner; 404 if class not found; 404 if not enrolled; 400 if the class is no longer SCHEDULED (already completed or cancelled); 200 on success; 500 on unexpected error.

## Sprint Reports
Status as of 2026-09-06. All six core modules are Complete. "Implemented" = built and passing automated checks (tsc / lint / 623 tests); manual QA items tracked in docs/TOTEST.txt.
SPRINT 1 | Authentication & Account Foundation
Goal | Establish secure identity, session handling, and access control that every other feature depends on.
Overall status | Complete
Features | 4 in this sprint - 4 done, 0 built, 0 partly done, 0 not started
Progress | 100% complete
Done | User Registration, User Login/Logout, Route Protection / Proxy Middleware, Account Management for Tutor and Learner
Built, needs testing | None
Partly done | None
Not started | None
Summary | Complete. Sign-up gives every learner and tutor a private STU-/TUT- ID, Bcrypt-hashed passwords and a recorded data-privacy consent. Login/logout and edge-of-network role guards work. Account settings are now finished for both roles: a read-only profile page plus a dedicated edit page where users update their own grade level, section and contact info (with PH-mobile validation), and a password can be reset from a link emailed to the user. Real name and email stay admin-only on purpose - they are the double-blind identity anchor.
SPRINT 2 | Class Lifecycle & Enrollment
Goal | Give tutors the tools to run classes and give learners the ability to find and join them.
Overall status | Complete (Schedule Table: tutor done, no combined learner view)
Features | 5 in this sprint - 4 done, 1 implemented, 0 partly done, 0 not started
Progress | about 96% complete
Done | Class Management for Tutor, Class Browsing for Learners, Learner Class Enrollment, Student Management for Tutors
Built, needs testing | None
Implemented | Schedule Table for Tutor and Learner
Not started | None
Summary | Tutors create classes with multiple sessions, publish/unpublish, edit and delete them, with clash detection, capacity limits, moderation and an appeal channel. Learners browse and filter classes, use a global quick-search, and join or leave a class. Tutors get an aggregated roster of everyone enrolled with them. The schedule view is a Mon-Sun timetable on the tutor dashboard and per-class session lists for learners; a single combined learner timetable page is the one piece still outstanding.
SPRINT 3 | Matching & Topic Requests
Goal | Connect learners to the right tutor automatically, and capture demand when no match exists.
Overall status | Complete
Features | 2 in this sprint - 2 done, 0 built, 0 partly done, 0 not started
Progress | 100% complete
Done | Automatic Tutor Matching, Class Request for Learners
Built, needs testing | None
Partly done | None
Not started | None
Summary | Complete. The weighted match-maker ranks live classes for a learner by subject, requested and verified topics, grade compatibility and schedule fit, with a one-on-one / group preference, shown on /learner/match. When nothing fits, the learner posts a class request (public or aimed at one tutor); a tutor accepts it and the system builds the class, with a full request lifecycle, notifications and an admin moderation queue.
SPRINT 4 | Assessment & Learning Measurement
Goal | Certify tutor competence per topic and measure learner progress through pre/post testing.
Overall status | Complete
Features | 4 in this sprint - 4 done, 0 built, 0 partly done, 0 not started
Progress | 100% complete
Done | Topic Assessment for Tutor, Topic Assessment Request for Tutor, Pre- and Post-Test Engine for Classes, Learner Progress Report
Built, needs testing | None
Partly done | None
Not started | None
Summary | Complete. The tutor knowledge test is a real auto-graded quiz drawn from an admin question bank with one platform-wide config; passing certifies the topic automatically or after a quick admin confirmation, and a tutor can now sit an assessment for any topic without first creating a class. The before/after tests were re-scoped to one test per session, taken twice, with per-question and per-learner pre->post reporting for tutor, admin and learner, plus a dedicated cross-class /learner/progress page. The 'no assessment yet' alert is a tutor-initiated request that notifies every admin - the thesis's automatic trigger was replaced by certification gating on class creation.
SPRINT 5 | Chatbot Assistant
Goal | Provide guided, rule-based in-app help for navigation, FAQs, and class recommendations.
Overall status | Complete
Features | 1 in this sprint - 1 done, 0 built, 0 partly done, 0 not started
Progress | about 95% complete
Done | Chatbot Assistant
Built, needs testing | None
Partly done | None
Not started | None
Summary | Built as a rule-based intent matcher - no AI. It tokenises the message, scores it against about 35 role-aware intents and a 26-entry FAQ with typo tolerance and a confidence gate, and replies with a canned answer, a deep link, or (for learners) live class matches. A floating widget in every portal keeps a local transcript that is wiped on sign-out, and unmatched questions are logged for an admin to review. The remaining work is growing the FAQ from real TRIS stakeholder interviews.
SPRINT 6 | Dashboards, Administration & Reporting
Goal | Surface consolidated views for every role and give admins moderation and oversight tools.
Overall status | Complete (except user-submitted Reports)
Features | 5 in this sprint - 4 done, 0 built, 0 partly done, 1 not started
Progress | about 92% complete
Done | Tutor Dashboard, Learner Dashboard, Admin Dashboard, User Management for Admin
Built, needs testing | None
Partly done | None
Not started | Report Class, Report Tutor, Report Learner
Summary | The three home dashboards are finished: the tutor sees stat cards with icons, an upcoming-sessions list and a Mon-Sun timetable; the learner sees enrolment stats, upcoming sessions and quick links; the admin sees platform counts plus a separate analytics page with charts (users, classes, certifications, a 30-day enrolment trend). Admins can suspend or ban accounts and classes, everything is written to an audit log, and tutors can appeal a class moderation (which notifies every admin). The one unbuilt item is letting users file a report against a class, tutor or learner - it is outside the six core modules and the need is met by admin moderation, the audit log and the appeal channel.

## Change Log
Feature | Original planning sheet | Current status | What changed / evidence
Account Management for Tutor and Learner | Partial | Complete | Learner profile now editable; both roles get a dedicated /{role}/profile/edit page; self-service grade level added; password-reset-by-email flow added.
Class Management for Tutor | Implemented (needs testing) | Complete | Verified in use across sprints; added certification-gated topic picker, finished-class lock, suspended-class action lockdown, and a tutor appeal channel.
Class Browsing for Learners | Partial | Complete | Global quick-search (Cmd/Ctrl+K, role-scoped) and a /learner/tutors directory added; unpublished-class placeholder for enrolled learners.
Learner Class Enrollment | Implemented (needs testing) | Complete | Enrol / drop now fires tutor notifications; route tests green.
Schedule Table for Tutor and Learner | Not Yet Started | Implemented | New WeeklyTimetable (Mon-Sun grid) on the tutor dashboard; learner still per-class + a progress page (no combined timetable).
Student Management for Tutors | Implemented (needs testing) | Complete | 'Enrolled In' column switched from subject to class code.
Automatic Tutor Matching | Not Yet Started | Complete | rankMatches() engine + /learner/match UI + admin kill switch shipped (Changes.md Part 5; refined Part 31).
Class Request for Learners (was 'Topic Request') | Not Yet Started | Complete | Full public / directed lifecycle, accept-to-class, notifications, admin moderation, Directed / Public / Accepted tabs; renamed from 'topic request' in the UI.
Topic Assessment for Tutor | Implemented (needs testing) | Complete | Per-(subject,topic) config replaced by one global config; take-assessment-without-a-class added; admin bank moved under /admin/assessment/.
Topic Assessment Request for Tutor | Partial | Complete (divergence) | Every active admin now notified on a request (QUESTION_REQUEST_NEW); the auto-trigger on class creation was intentionally replaced by certification gating.
Pre- and Post-Test Engine for Classes | Implemented (needs testing) | Complete | Re-grained from ClassTest (one per class) to SessionTest (one per session, served twice); landed on main with seed data + admin / tutor / learner UI (Part 29, phases 0-8).
Learner Progress Report | Partial | Complete | Dedicated cross-class /learner/progress page + tutor ClassProgressPanel + admin results view.
Chatbot Assistant | Not Yet Started | Complete | Deterministic intent matcher, per-portal widget, admin misses review, usability pass (Changes.md Parts 19 and 30).
Tutor Dashboard | Partial | Complete | Stat-card icons, readable upcoming-sessions list, WeeklyTimetable.
Learner Dashboard | Partial | Complete | Enrolment stats, upcoming-sessions list, quick links.
Admin Dashboard | Partial | Complete | Overview + full /admin/reports analytics (charts) + AuditLog.
User Management for Admin | Implemented (needs testing) | Complete | Sortable tables (including a Code column), class-appeal workflow with an audit-log link + admin notification, DECLINED registration state.
Report Class, Report Tutor, Report Learner | Not Yet Started | Not Yet Started | Unchanged - deprioritised, outside the six core modules; covered by admin moderation + AuditLog + the appeal channel.