## Feature Status
Sprint | Feature | Description | Status | Notes / Implementation Detail (verified 2026-09-02)
1 | User Registration | Auto-generates unique student and tutor IDs, validates input using Zod, hashes passwords with Bcrypt, and captures Data Privacy Act consent during sign-up via a dedicated registration form. | Complete | Unified RegisterForm + POST /api/register (Zod discriminated union on type LEARNER/TUTOR). Atomic STU-/TUT- ID counters via generateAnonymousId, Bcrypt hashing, consentGiven captured, TutorProfile created in the same transaction. Gated by registrationOpen platform setting.
1 | User Login/Logout | Handles user authentication through NextAuth's credentials provider, using JWT-based sessions and Bcrypt password comparison for secure login and logout. | Complete | NextAuth credentials provider, JWT sessions, Bcrypt compare (src/lib/auth.ts). Sign-out via /api/auth/signout. Unchanged.
1 | Route Protection / Proxy Middleware | Enforces server-side role validation across all portals and API routes to prevent unauthorized access. | Complete | src/proxy.ts edge middleware guards /admin, /tutor, /learner; every API route re-checks getServerSession + role. Unchanged.
1 | Account Management for Tutor and Learner | Allows tutors and learners to view and update their account details, including profile information and credentials, after registration. | Partial | Tutor side built: /tutor/profile page + ProfileEditForm + PATCH /api/tutor/profile (edits contactInfo & section; validations/profile.ts). Learner side unchanged: /learner/profile is still read-only, no learner profile API. Email/password change flow not built for either role. | need to finalize profile pages what info to display, layout and edit
2 | Class Management for Tutor | Provides a UI for tutors to create, view, update, and delete classes, supporting both one-on-one and group (one-to-many) tutoring sessions. | Implemented but needs testing | Full create/edit/delete for classes, each holding multiple sessions. Includes class detail and edit pages, publish/unpublish, capacity limits, cross-class schedule-conflict checks, status cascade to sessions, and optional certification gating. Code complete; not yet tested.
2 | Class Browsing for Learners | Lets learners search and browse available classes, with filters by topic, schedule, and subject. | Partial | Browse page and class-detail page exist, with session lists, verified-topic badges, a tutor profile modal, and auto-reinstatement of expired suspensions. Still missing: search and filters by subject, topic, or schedule.
2 | Learner Class Enrollment | Enables learners to enroll in or unenroll from a tutor's class. | Implemented but needs testing | POST + DELETE /api/classes/[classId]/enroll with full edge-case handling (not SCHEDULED, no upcoming session, full, already enrolled, unenroll blocked on completed/cancelled). LearnerClassActions component; route tests present. Not yet verified end-to-end.
2 | Schedule Table for Tutor and Learner | Displays a schedule table showing each user's upcoming and ongoing classes. | Not Yet Started
2 | Student Management for Tutors | Allows tutors to manage the list of learners enrolled in their classes. | Implemented but needs testing | A /tutor/students page lists all anonymized learners across the tutor's classes, with per-enrollment subject/topic/date detail, filters (grade, section, subject, class), pagination, and a profile drill-in. Not yet tested.
3 | Automatic Tutor Matching | Matches learners with suitable tutors using a weighted scoring algorithm based on subject, topic, grade level, and schedule compatibility, presented through a dedicated UI. | Not Yet Started
3 | Topic Request for Learners | Allows learners to submit a request specifying their desired topic, subject, and preferred schedule when no suitable tutor match is found. | Not Yet Started
4 | Topic Assessment for Tutor | Evaluates a tutor's subject knowledge for topics they intend to teach; tutors who pass are awarded a badge for that topic, supported by a question bank. | Implemented but needs testing | Now includes the actual knowledge test. Admin question bank per subject+topic (/admin/question-bank) with per-topic config (question count, pass %, min bank size). Tutors take an auto-graded single-answer MCQ quiz from the bank; retakes prefer unseen questions. Passing certifies the topic - automatically when the autoCertifyOnAssessmentPass platform setting is on, otherwise a pending certification is raised for admin confirmation; failing marks it not-passed with a retake note. Attempt history for the tutor, full per-question results for the admin. Route + lib tests present; walked through in-app but not full QA.
4 | Topic Assessment Request for Tutor | Notifies the admin when a tutor creates a class for a topic that has no existing assessment, prompting the admin to create one so all topics remain properly assessed. | Partial | A QuestionRequest model + 'Request questions' action on the tutor Assessments page now let a tutor ask an admin to stock a thin/empty topic; requests appear in an admin queue (/admin/question-bank Requests tab) and on the admin dashboard ('Open question requests'), and can be resolved/dismissed. Still missing the spec's automatic trigger: creating a class for an unassessed topic does not open a request - it is gated/rejected by requireCertificationForClassCreation instead.
4 | Pre- and Post-Test Engine for Classes | Requires tutors to publish pre- and post-session quizzes to measure student understanding and track learning progress. | Implemented but needs testing | Built. A tutor creates one PRE and one POST test per class from admin-bank questions and/or their own custom questions (ClassTestBuilder: add-from-bank, my-questions, write-a-question, reorder, publish, close). Enrolled learners take each test once (single attempt, auto-graded, own results with right/wrong + explanations). Tutor and admin see per-learner results with a pre->post delta and class averages; per-attempt drill-down. Tutor custom questions are isolated from the admin bank and the certification pool (origin flag). 8 new Vitest files; not yet full QA.
4 | Learner Progress Report | Provides a before-and-after comparison of learner scores to visualize academic progress. | Partial | The pre->post comparison now exists as part of the Pre/Post-Test Engine: the class-test results view (tutor + admin) shows each learner's pre score, post score, improvement delta and class averages, and the learner sees their own scores on the class page. Missing a dedicated, cross-class learner-facing progress report / visualisation.
5 | Chatbot Assistant | Uses intent-based response logic (rule/pattern matching) to identify user requests, offering navigation help, FAQ support, class recommendations, and an interactive chat widget. | Not Yet Started
6 | Tutor Dashboard | Displays a tutor's classes, schedule, and other relevant account information in one view. | Partial | The /tutor landing page shows stats (topics taught, verified topics, pending requests), an onboarding checklist, and an assessments summary card. It does not yet show the tutor's class list or schedule - those live on separate pages.
6 | Learner Dashboard | Displays a learner's classes, schedule, and other relevant account information in one view. | Partial | The /learner landing page is a placeholder - an anonymized ID badge and a 'Browse Classes' button only. No enrolled-class list, schedule, or stats yet.
6 | Admin Dashboard | Presents platform-wide information such as total learners, tutors, and created classes, along with system status and usage statistics. | Partial | Not final. /admin shows 4 counts (learners, tutors, flagged accounts, active classes) plus a static welcome card - no system-status panel, no charts, no usage stats beyond the counts. Richer analytics live on the separate /admin/reports page. Layout still provisional.
6 | User Management for Admin | Allows the admin to suspend a class or suspend/ban a tutor or learner account. | Implemented but needs testing | Admins can suspend or ban accounts (with a suspend duration) and suspend classes, via /admin/users and /admin/classes. Expired suspensions lift automatically and every action is written to AuditLog. Not yet tested.
6 | Report Class, Report Tutor, Report Learner | Enables users to submit reports on classes, tutors, or learners, notifying the admin for review. | Not Yet Started
| TOTALS | 21 features — 3 Complete, 6 Implemented (needs testing), 7 Partial, 5 Not Yet Started
Weighted progress (Complete 1.0 / Needs-testing 0.8 / Partial 0.5): 54%
Original planning sheet: 3 Complete, 6 Partial, 12 Not Yet Started.
TODO:
style signout fallbacl
check unauthorize fallback page
check proxy/middle ware
OPEN QUESTIONS / ANSWERS
| Q (Learner Class Enrollment): | What are the edge cases?
| A - enroll (POST): | 401 if not a logged-in learner; 404 if class not found; 400 if the class is not SCHEDULED or not published; 400 if it has no upcoming SCHEDULED session in the future; 409 if the class is full (enrollments >= maxStudents); 409 if already enrolled; expired class suspensions are auto-reinstated before the checks; 500 on unexpected error.
| A - unenroll (DELETE): | 401 if not a logged-in learner; 404 if class not found; 404 if not enrolled; 400 if the class is no longer SCHEDULED (already completed or cancelled); 200 on success; 500 on unexpected error.

## Sprint Reports
Status as of 2026-09-02. "Built, needs testing" means the feature is coded but not yet checked; "Partly done" means some of it works and some is still missing.
SPRINT 1 | Authentication & Account Foundation
Goal | Establish secure identity, session handling, and access control that every other feature depends on.
Overall status | In Progress
Features | 4 in this sprint — 3 done, 0 built (needs testing), 1 partly done, 0 not started
Progress | about 88% complete
Done | User Registration, User Login/Logout, Route Protection / Proxy Middleware
Built, needs testing | None
Partly done | Account Management for Tutor and Learner
Not started | None
Summary | Done and working. Students and tutors can sign up, and the system gives each person a private ID so real names stay hidden. Passwords are stored securely and everyone agrees to the data-privacy notice when they join. Logging in and out works, and every page checks that the person is allowed to be there. The one unfinished piece is account settings: tutors can edit their contact details and section, but learners can't edit anything yet, and no one can change their email or password from inside the app.
SPRINT 2 | Class Lifecycle & Enrollment
Goal | Give tutors the tools to run classes and give learners the ability to find and join them.
Overall status | In Progress
Features | 5 in this sprint — 0 done, 3 built (needs testing), 1 partly done, 1 not started
Progress | about 58% complete
Done | None
Built, needs testing | Class Management for Tutor, Learner Class Enrollment, Student Management for Tutors
Partly done | Class Browsing for Learners
Not started | Schedule Table for Tutor and Learner
Summary | Most of it is built but still needs testing before we call it finished. Tutors can create a class, give it several meeting times, edit it, show or hide it from learners, and delete it, and the system stops two sessions from clashing. Learners can join and leave a class. Tutors also have a page that lists every student enrolled with them, with search and filters. Two things are still open: the class list has no filters yet (you can only scroll it), and there is no single timetable showing everyone's upcoming classes in one place.
SPRINT 3 | Matching & Topic Requests
Goal | Connect learners to the right tutor automatically, and capture demand when no match exists.
Overall status | Not Yet Started
Features | 2 in this sprint — 0 done, 0 built (needs testing), 0 partly done, 2 not started
Progress | about 0% complete
Done | None
Built, needs testing | None
Partly done | None
Not started | Automatic Tutor Matching, Topic Request for Learners
Summary | Not started. This is the automatic match-maker that suggests the best tutor for a learner based on subject, year level, and schedule, plus a way for learners to post what they need when no tutor fits.
SPRINT 4 | Assessment & Learning Measurement
Goal | Certify tutor competence per topic and measure learner progress through pre/post testing.
Overall status | In Progress
Features | 4 in this sprint — 0 done, 2 built (needs testing), 2 partly done, 0 not started
Progress | about 65% complete
Done | None
Built, needs testing | Topic Assessment for Tutor, Pre- and Post-Test Engine for Classes
Partly done | Topic Assessment Request for Tutor, Learner Progress Report
Not started | None
Summary | Big jump this cycle. The tutor knowledge test is now real: an admin-run question bank per topic and an auto-graded quiz, with passing tutors certified automatically or after a quick admin confirmation. The before-and-after class quizzes are also built - a tutor assembles a pre-test and a post-test from bank or self-written questions, learners take each once, and tutors and admins get a per-learner before/after comparison with class averages. Both still need a full test pass. Still open: the request that alerts an admin is tutor-initiated, not automatic on class creation, and there is no separate cross-class learner progress report yet.
SPRINT 5 | Chatbot Assistant
Goal | Provide guided, rule-based in-app help for navigation, FAQs, and class recommendations.
Overall status | Not Yet Started
Features | 1 in this sprint — 0 done, 0 built (needs testing), 0 partly done, 1 not started
Progress | about 0% complete
Done | None
Built, needs testing | None
Partly done | None
Not started | Chatbot Assistant
Summary | Not started. A simple in-app assistant that answers common questions and helps people find their way around, using set replies rather than AI.
SPRINT 6 | Dashboards, Administration & Reporting
Goal | Surface consolidated views for every role and give admins moderation and oversight tools.
Overall status | In Progress
Features | 5 in this sprint — 0 done, 1 built (needs testing), 3 partly done, 1 not started
Progress | about 46% complete
Done | None
Built, needs testing | User Management for Admin
Partly done | Tutor Dashboard, Learner Dashboard, Admin Dashboard
Not started | Report Class, Report Tutor, Report Learner
Summary | In progress, nothing finished yet. Admins can suspend or ban accounts and suspend classes, and a record is kept of every action (still needs testing). There is a separate admin analytics page with platform totals and charts. The three home dashboards are only part done: the admin one shows four numbers and little else and its layout is not final, the tutor one shows a few stats, and the learner one is just a welcome screen. Letting users report a class, tutor, or learner has not been started.

## Change Log
Feature | Original planning sheet | Current status | What changed / evidence
Account Management for Tutor and Learner | Partial | Partial | Tutor profile page + PATCH /api/tutor/profile added (edit contactInfo/section). Learner side still read-only.
Class Management for Tutor | Partial | Implemented but needs testing | Refactored to course-container + multi-session model; full CRUD, detail/edit pages, publish/unpublish, conflict detection, capacity guards, status cascade. Not yet verified.
Learner Class Enrollment | Partial | Implemented but needs testing | DELETE /enroll (unenroll) added with completed/cancelled guard; all enroll edge cases covered. Not yet verified end-to-end.
Student Management for Tutors | Not Yet Started | Implemented but needs testing | New /tutor/students page + GET /api/tutor/students (aggregated, filtered, paginated) + roster and profile-modal components. Not yet verified.
Class Browsing for Learners | Partial | Partial | Detail pages, verified-topic signal, tutor profile modal, auto-reinstatement added — subject/topic/schedule filter UI still missing.
Topic Assessment for Tutor | Not Yet Started | Implemented but needs testing | Question bank (/admin/question-bank) + per-topic config + auto-graded single-answer MCQ quiz added; passing certifies automatically (autoCertifyOnAssessmentPass setting) or raises a pending certification for admin confirmation. Attempt history + admin results view. Was manual-only certification before.
Topic Assessment Request for Tutor | Not Yet Started | Partial | QuestionRequest model + tutor 'Request questions' flow + admin Requests queue + 'Open question requests' dashboard tile now exist. Still not auto-triggered by class creation (rejected/gated instead).
Tutor Dashboard | Not Yet Started | Partial | /tutor page now shows stats, onboarding checklist, assessments summary card; no class list/schedule on the dashboard yet.
Learner Dashboard | Not Yet Started | Partial | /learner page exists as a placeholder (ID badge + Browse CTA); no class list/schedule/stats yet.
Admin Dashboard | Not Yet Started | Partial | CORRECTION — an earlier draft of this sheet said Complete. /admin shows 4 raw counts + a static welcome card only: no system-status panel, no usage stats beyond counts. Richer analytics live on the separate /admin/reports page. Content not final.
User Management for Admin | Not Yet Started | Implemented but needs testing | /admin/users + /admin/classes with suspend/ban (+ duration), suspend class, AuditLog, expired-suspension auto-reinstatement. Not yet verified.
Schedule Table for Tutor and Learner | Not Yet Started | Not Yet Started | No change to the feature; the ClassSession model now provides the data layer it needs.
Pre- and Post-Test Engine for Classes | Not Yet Started | Implemented but needs testing | New: ClassTest (one PRE + one POST per class), tutor builder (admin-bank + custom questions), learner single-attempt take/review, tutor + admin results with pre->post delta and class averages. 8 new test files. Not yet full-QA'd.
Learner Progress Report | Not Yet Started | Partial | Per-class pre->post score comparison + class averages now shown in the class-test results view (tutor/admin); learner sees own scores on the class page. No dedicated cross-class learner progress report yet.